|  |  |  |
| --- | --- | --- |
| **Schedule for development of 2018 WCAC Report to the 86th Texas Legislature** | | |
| **MONTH** | **KEY DATES** | **DETAILS** |
| JAN | **January 17** | **Meeting: Council members provided Draft Report Outline and Schedule.** |
| FEB | **February 14** | **Meeting:** |
| MAR | **March 20** | **Meeting: Members asked to update sections for respective interests** |
| APR |  |  |
| MAY | **May 9** | **Meeting: Members review content for Legislative report** |
| May 30 | Send FIRST DRAFT to members by this date |
| JUN | **June 20** | **Meeting: Council members review FIRST DRAFT and take action on legislative recommendations** |
| JUL | July 11 | Deadline for providing new content or suggested revisions of FIRST DRAFT to TWDB |
| July 19 | Send SECOND DRAFT to members by this date |
| AUG | **TBD** | **Meeting: Council members approve SECOND DRAFT and provide suggested revisions** |
| August 10 | Send DRAFT to members for formal comments from State Agency & Interest Group Leadership |
| SEP | September 22 | DRAFT submitted to TWDB for editorial review |
| OCT | October 1 | Send FINAL DRAFT to members by this date |
| **TBD** | **Meeting: Council members review and vote to approve content of FINAL DRAFT** |
| October 31 | FINAL DRAFT submitted to TWDB for last editorial review and preparation of FINAL REPORT |
| NOV | November 15 | Deadline for receipt by TWDB Publications to print and bind copies |
| November 30 | Deliver Reports to Governor, Lieutenant Governor, and Speaker of the Texas House of Representatives. |
|  | *Last updated on March 28, 2018* | |